## Zone A
Green Streets sponsor |  |  |  | 2024 | [5 empty] | 2025
GRI ID | St Name | Address Description | Size | Jun 15-Jul 30 | Jun 15-Jul 31 | Aug 15-Sep 30 | Aug 15-Sep 31 | Oct 15-Nov 30 | Oct 15-Nov 31 | Feb 1-Mar 15 | Feb 1-Mar 16 | Apr 1-May 15 | Apr 1-May 16 | Total Cost | Total Visits | Total Cost/m2
130013 | Killarney St | At East 45th Ave, SE corner | 10.4 | 1 | 122.53 | 1 | 122.53 | 1 | 178.23 | 1 | 122.53 | 1 | 122.53 | 668.35 | 5 | 64.2644
120203 | E 45th Ave | At Inverness St, NE Corner | 12.6 | 0 | 0 | 1 | 122.53 | 1 | 178.23 | 1 | 122.53 | 1 | 122.53 | 545.82 | 4 | 43.319
120205 | Inverness | At E 45th Ave, Southwest Corner | 12.7 | 0 | 0 | 1 | 122.53 | 1 | 178.23 | 1 | 122.53 | 1 | 122.53 | 545.82 | 4 | 42.978
120204 | E 45th Ave | At Inverness St, SE Corner | 15.1 | 0 | 0 | 1 | 122.53 | 1 | 178.23 | 1 | 122.53 | 1 | 122.53 | 545.82 | 4 | 36.147
120042 | W 19th Ave | At Laurel St, SW Corner | 17.8 | 0 | 0 | 1 | 122.53 | 1 | 178.23 | 1 | 122.53 | 1 | 122.53 | 545.82 | 4 | 30.664
120108 | W 16th Ave | At Manitoba St (NE Corner) | 18.4 | 1 | 122.53 | 1 | 122.53 | 1 | 178.23 | 1 | 122.53 | 1 | 122.53 | 668.35 | 5 | 36.3234
110121 | Ontario Street | At 16th Ave, SW side | 19 | 1 | 122.53 | 1 | 122.53 | 1 | 178.23 | 1 | 122.53 | 1 | 122.53 | 668.35 | 5 | 35.1763
120037 | Kerr St | At E Kent Ave South, SW corner | 20.7 | 1 | 122.53 | 1 | 122.53 | 1 | 178.23 | 1 | 122.53 | 1 | 122.53 | 668.35 | 5 | 32.2874
120091 | Ontario St | At E 42nd Ave, NE Corner | 21.2 | 1 | 122.53 | 1 | 122.53 | 1 | 178.23 | 1 | 122.53 | 1 | 122.53 | 668.35 | 5 | 31.5259
120041 | W 19th Ave | At Laurel St, NW Corner | 21.3 | 0 | 0 | 1 | 122.53 | 1 | 178.23 | 1 | 122.53 | 1 | 122.53 | 545.82 | 4 | 25.6254
120061 | Sophia St | At E 13th Ave, NE Corner | 21.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 122.53 | 122.53 | 1 | 5.7526
120064 | Willow St | At W 16th Ave, NW corner | 22.7 | 1 | 122.53 | 1 | 122.53 | 1 | 178.23 | 1 | 122.53 | 1 | 122.53 | 668.35 | 5 | 29.4427
120056 | Rhodes St | At E 41st Ave, SW corner | 23.4 | 1 | 122.53 | 1 | 122.53 | 1 | 178.23 | 1 | 122.53 | 1 | 122.53 | 668.35 | 5 | 28.562
120034 | E 50th Ave | At Ontario St, SE Corner | 23.6 | 1 | 122.53 | 1 | 122.53 | 1 | 178.23 | 1 | 122.53 | 1 | 122.53 | 668.35 | 5 | 28.3199
120047 | W 49th Ave | At Maple St, NE Corner | 23.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 122.53 | 122.53 | 1 | 5.17
120063 | W 16th Ave | At Willow St, NE corner | 24.4 | 1 | 122.53 | 1 | 122.53 | 1 | 178.23 | 1 | 122.53 | 1 | 122.53 | 668.35 | 5 | 27.3914
130014 | E Kent Ave North | South side, between Kinross St and Pierview | 25.6 | 0 | 0 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 657.22 | 4 | 25.6727
130016 | E Kent Ave North | South side, across from stairs | 25.7 | 0 | 0 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 657.22 | 4 | 25.5728
120103 | Windsor St | At E 22nd Ave, SE Corner | 26.3 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 30.7072
120058 | Rhodes St | At E 41st Ave, SE corner | 27 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 29.9111
120102 | Windsor St | Between E 24th and E 23rd Ave | 28.5 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 28.3368
120052 | Nanaimo St | At E 40th Ave, SW Corner | 28.8 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 28.0417
120053 | Nanaimo St | At E 39th Ave, SW corner |  | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5
120087 | Riverwalk Ave | North side, in front of unit 107 | 29.6 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 27.2838
120086 | Riverwalk Ave | South side, across from unit 107 | 30.1 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 26.8306
130015 | E Kent Ave North | South side, across from 3187 | 30.3 | 0 | 0 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 657.22 | 4 | 21.6904
120072 | Sawmill Crescent E | In front of Public Eatery | 30.6 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 26.3922
120099 | W 59th Ave | At Ross St | 30.6 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 26.3922
120085 | Riverwalk Ave | North side, in front of unit 113 | 31.1 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 25.9678
130017 | E Kent Ave North | South side, across from 3131 | 33.2 | 0 | 0 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 657.22 | 4 | 19.7958
120084 | Riverwalk Ave | South side, west of 3162 | 33.6 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 24.0357
120082 | Riverwalk Ave | North side, in front of unit 109 | 35.3 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 22.8782
120076 | Sawmill Crescent E | At Rivergrass Dr, SW corner | 35.7 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 22.6218
120088 | E 57th Ave | At Ross St, Southwest Corner | 36.1 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 22.3712
120060 | W 42nd Ave | At Ontario St, SE Corner | 36.9 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 21.8862
120081 | Riverwalk Ave | At Kerr St, SE corner | 37.4 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 21.5936
120075 | Sawmill Crescent E | At Rivergrass Dr, NW corner | 37.6 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 21.4787
120214 | E Kent Ave North | North side of Kent, closer to Rivergrass Dr | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 150.38 | 150.38 | 1 | 3.9574
120083 | Riverwalk Ave | South side, in front of 3138 | 38.3 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 21.0862
120080 | Riverwalk Ave | At Kerr St, NE corner | 42.1 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 19.1829
120074 | Sawmill Crescent E | In front of 3538 | 48.4 | 1 | 150.38 | 1 | 150.38 | 1 | 206.08 | 1 | 150.38 | 1 | 150.38 | 807.6 | 5 | 16.686
120073 | Sawmill Crescent E | In front of 3557 | 53.2 | 1 | 334.18 | 1 | 334.18 | 1 | 573.67 | 1 | 334.18 | 1 | 334.18 | 1910.39 | 5 | 35.9096
120094 | Ontario St | At E 43rd Ave, NE Corner | 72.2 | 1 | 334.18 | 1 | 334.18 | 1 | 573.67 | 1 | 334.18 | 1 | 334.18 | 1910.39 | 5 | 26.4597
120215 | E Kent Ave North | North side of Kent, closer to Boundary | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 334.18 | 334.18 | 1 | 4.5778
110007 | Pierview Crescent | At East Kent Ave North, Northerly Bioswale closer to turning circle | 74.7 | 1 | 334.18 | 1 | 334.18 | 1 | 573.67 | 1 | 334.18 | 1 | 334.18 | 1910.39 | 5 | 25.5742
120092.93 | Ontario St | At E 42nd Ave, NW Corner | 110.9 | 1 | 470 | 1 | 470 | 1 | 650 | 1 | 470 | 1 | 470 | 2530 | 5 | 22.8133
110006 | Pierview Crescent | At East Kent Ave North, NW Corner | 111.3 | 1 | 470 | 1 | 470 | 1 | 650 | 1 | 470 | 1 | 470 | 2530 | 5 | 22.7314
110109 | Cambie St | Between McGuigan and W 35th Ave | 232.7 | 1 | 990 | 1 | 990 | 1 | 1390 | 1 | 990 | 1 | 990 | 5350 | 5 | 22.991
110108.116 | Prince Edward St | Between E 51st Ave and E 53rd Ave @ Sunset Park | 377.2 | 1 | 990 | 1 | 990 | 1 | 1390 | 1 | 990 | 1 | 990 | 5350 | 5 | 14.1835
49 |  |  | 2210.3 | 36 | 8032.91 | 45 | 9247.08 | 45 | 13242.15 | 45 | 9247.08 | 49 | 9976.7 | 49745.92 | 220 | 25.8034
[5 empty] | 30522.14 |  |  | 46832.4 |  |  |  | 2023 vs 2024 |  |  | May 2023-2024 vs May 2024-2025
[12 empty] | 0.08318 |  |  | 0.15057
[5 empty] | Season | <25 m² | 25-50 m² | 50-100 m² | 100-150 m² | >150 m² |  | Season | <25 m² | 25-50 m² | 50-100 m² | 100-150 m² | >150 m²
[5 empty] | Spring | 122.53 | 150.38 | 334.18 | 587 | 1198 |  | Spring | 122.53 | 150.38 | 334.18 | 470 | 990
[5 empty] | Summer | 122.53 | 150.38 | 334.18 | 587 | 1198 |  | Summer | 122.53 | 150.38 | 334.18 | 470 | 990
[5 empty] | Fall | 178.23 | 206.08 | 573.67 | 892 | 1821 |  | Fall | 178.23 | 206.08 | 573.67 | 650 | 1390
[5 empty] | Winter | 122.53 | 150.38 | 334.18 | 587 | 1198 |  | Winter | 122.53 | 150.38 | 334.18 | 470 | 990
[6 empty] | 45.46% | 22.73% | 122.2% | 75.65% | 104.1% |  |  | 45.46% | 22.73% | 122.2% | 40.64% | 110.6%
[7 empty] | 15.63% | 178.4% | 55.49% | 104.1% |  |  |  | 15.63% | 178.4% | 13.31% | 113.8%
[5 empty] | Season | <25 m² |  | 25-50 m² |  | 50-100 m² |  | 100-150 m² |  | >150 m²
[6 empty] | Low End | High End | Low End | High End | Low End | High End | Low End | High End | Low End | High End
[5 empty] | Fall | 17.1375 | 7.3045 | 8.05 | 4.1886 | 10.7833 | 7.6797 | 8.0433 | 6.4826 | 11.817 | 4.8277
[5 empty] | Other | 11.7817 | 5.0217 | 5.8742 | 3.0565 | 6.2816 | 4.4736 | 5.2931 | 4.266 | 7.7742 | 3.176
[5 empty] | Season | <25 m² | 25-50 m² | 50-100 m² | 100-150 m² | >150 m²
[5 empty] | Fall | 12.221 | 6.1193 | 9.2315 | 7.2629 | 8.3223
[5 empty] | Other | 8.4017 | 4.4654 | 5.3776 | 4.7795 | 5.4751

## Zone B
Green Streets sponsor |  |  |  | 2024 | [5 empty] | 2025
GRI ID | St Name | Address Description | Size | Jun 15-Jul 30 | Jun 15-Jul 31 | Aug 15-Sep 30 | Aug 15-Sep 31 | Oct 15-Nov 30 | Oct 15-Nov 31 | Feb 1-Mar 15 | Feb 1-Mar 16 | Apr 1-May 15 | Apr 1-May 16 | Total Cost | Total Visits | Total Cost/m2
310103 | Richards St | Between Dunsmuir St and W Georgia St - Block A RTT (13xStandard) | 2.16 | 1 | 260 | 0 | 0 | 1 | 260 | 0 | 0 | 1 | 260 | 780 | 3
310105 | Richards St | Between Robson St and Smithe St - Block C RTT (11xStandard) | 2.16 | 1 | 220 | 0 | 0 | 1 | 220 | 0 | 0 | 1 | 220 | 660 | 3
310107 | Richards St | Between Smithe St and Nelson St - Block D RTT (14xStandard) | 2.16 | 1 | 280 | 0 | 0 | 1 | 280 | 0 | 0 | 1 | 280 | 840 | 3
320105 | Richards St | Between W Georgia St and Robson St - Block B RTT (11xStandard) | 2.16 | 1 | 220 | 0 | 0 | 1 | 220 | 0 | 0 | 1 | 220 | 660 | 3
320107 | Richards St | Between Helmcken St. and Nelson St. - Block E RTT (13xComplex) | 2.16 | 1 | 390 | 1 | 390 | 1 | 390 | 1 | 390 | 1 | 390 | 1950 | 5
320108 | Richards St | Between Davie St. and Helmcken St. - Block F RTT (10xComplex) | 2.16 | 1 | 300 | 1 | 300 | 1 | 300 | 1 | 300 | 1 | 300 | 1500 | 5
320109 | Richards St | Between Drake St. and Davie St. - Block G RTT (13xComplex) | 2.16 | 1 | 390 | 1 | 390 | 1 | 390 | 1 | 390 | 1 | 390 | 1950 | 5
320110 | Richards St | Between Pacific St. and Drake St. - Block H RTT (12xComplex) | 2.16 | 1 | 360 | 1 | 360 | 1 | 360 | 1 | 360 | 1 | 360 | 1800 | 5
120024 | E 15th | at Dumfries St, NE Corner | 8.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 346.49 | 346.49 | 1 | 41.2488
120057 | Trafalgar St | At Broadway, SW Corner | 11.6 | 1 | 230.99 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1385.95 | 5 | 119.4784
120021 | Comox St | At Gilford St, SW Corner | 12.6 | 0 | 0 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1154.96 | 4 | 91.6635
120201 | Campbell Ave | At Union St, NW Corner | 13.3 | 1 | 230.99 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1385.95 | 5 | 104.2068
120040 | Larch St | At Broadway, SW Corner | 13.6 | 1 | 230.99 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1385.95 | 5 | 101.9081
120003 | Balsam St | At E Broadway, NW Corner | 14.8 | 0 | 0 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1154.96 | 4 | 78.0378
120059 | Trafalgar St | At Broadway, SE Corner | 15.3 | 1 | 230.99 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1385.95 | 5 | 90.585
120098 | Tisdall St | At W 48 Ave, Northwest Corner | 16.6 | 1 | 230.99 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1385.95 | 5 | 83.491
120001 | Arbutus St | At W 8th, NW Corner | 17.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 346.49 | 346.49 | 1 | 20.2626
120209 | Haro Street | Haro Street at Broughton Street | 17.2 | 1 | 230.99 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1385.95 | 5 | 80.5785
120097 | Tisdall St | At W 48 Ave, Northeast Corner | 17.3 | 1 | 230.99 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1385.95 | 5 | 80.1127
130104 | Gilford Street | Gilford Street between Haro Street and Rosemary Brown Lane | 17.4 | 1 | 230.99 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1385.95 | 5 | 79.6523
120213 | Cook St. | At W 1st Ave, SW corner | 18 | 1 | 230.99 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1385.95 | 5 | 76.9972
120002 | Arbutus St | At W 8th, NE Corner | 18.1 | 1 | 230.99 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1385.95 | 5 | 76.5718
120107 | Woodland Dr | At E 14th Ave, SE Corner | 18.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 346.49 | 346.49 | 1 | 19.0379
120089 | E 14th Ave | At Woodland Dr, NE Corner | 19.2 | 0 | 0 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1154.96 | 4 | 60.1542
120090 | E 14th Ave | At Woodland Dr, SE Corner | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 346.49 | 346.49 | 1 | 17.3245
120054 | Nicola St | At Comox St, SW Corner | 20.4 | 0 | 0 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1154.96 | 4 | 56.6157
120018 | Charles St | At Penticton St, NE Corner | 20.8 | 1 | 230.99 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1385.95 | 5 | 66.6322
120106 | Woodland Dr | At E 14th Ave, SW Corner | 21.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 346.49 | 346.49 | 1 | 16.2671
120105 | Woodland Dr | At E 14th Ave, NE Corner | 21.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 346.49 | 346.49 | 1 | 16.1911
120004 | Balsam St | At W 6th Ave, NW corner | 22.1 | 0 | 0 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1154.96 | 4 | 52.2606
110102 | E 1st Ave | At Quebec Street, Northwest Corner | 22.2 | 1 | 230.99 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1385.95 | 5 | 62.4302
120104 | Woodland Dr | At E 14th Ave, NW Corner | 22.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 346.49 | 346.49 | 1 | 15.6077
120022 | Comox St | At Nicola St, NE Corner | 22.6 | 0 | 0 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1154.96 | 4 | 51.1044
120208 | W 7th Ave | At Pine St, NE Corner | 24.3 | 1 | 230.99 | 1 | 230.99 | 1 | 346.49 | 1 | 230.99 | 1 | 346.49 | 1385.95 | 5 | 57.035
120207 | Pine St | At W 7th Ave, SE Corner | 25.2 | 1 | 276.19 | 1 | 276.19 | 1 | 414.29 | 1 | 276.19 | 1 | 414.29 | 1657.15 | 5 | 65.7599
120206 | W 8th Ave | At Pine St, NE Corner | 25.2 | 1 | 276.19 | 1 | 276.19 | 1 | 414.29 | 1 | 276.19 | 1 | 414.29 | 1657.15 | 5 | 65.7599
110105 | Quebec St | At E 1st Avenue, Northeast Corner | 26.5 | 1 | 276.19 | 1 | 276.19 | 1 | 414.29 | 1 | 276.19 | 1 | 414.29 | 1657.15 | 5 | 62.534
110117 | Haro Street | Haro Street at Bute Street | 27.7 | 1 | 276.19 | 1 | 276.19 | 1 | 414.29 | 1 | 276.19 | 1 | 414.29 | 1657.15 | 5 | 59.8249
120020 | Comox St | At Bute St, NW Corner | 29.2 | 0 | 0 | 1 | 276.19 | 1 | 414.29 | 1 | 276.19 | 1 | 414.29 | 1380.96 | 4 | 47.2932
120062 | W 12th Ave | At Trafalgar St, SE Corner | 29.2 | 1 | 276.19 | 1 | 276.19 | 1 | 414.29 | 1 | 276.19 | 1 | 414.29 | 1657.15 | 5 | 56.7517
110106 | Quebec St | At E 1st Avenue, Southeast Corner | 30.8 | 1 | 276.19 | 1 | 276.19 | 1 | 414.29 | 1 | 276.19 | 1 | 414.29 | 1657.15 | 5 | 53.8036
120019 | Comox St | At Bidwell St, NE Corner | 31 | 0 | 0 | 1 | 276.19 | 1 | 414.29 | 1 | 276.19 | 1 | 414.29 | 1380.96 | 4 | 44.5471
110107 | Quebec St | At Switchmen Street, Northeast Corner | 32.5 | 1 | 276.19 | 1 | 276.19 | 1 | 414.29 | 1 | 276.19 | 1 | 414.29 | 1657.15 | 5 | 50.9892
120210 | Haro Street | Haro Street at Jervis Street | 33.9 | 1 | 276.19 | 1 | 276.19 | 1 | 414.29 | 1 | 276.19 | 1 | 414.29 | 1657.15 | 5 | 48.8835
130006 | E 8th Ave | At Grandview Hwy (turning circle) | 41.3 | 0 | 0 | 1 | 276.19 | 1 | 414.29 | 1 | 276.19 | 1 | 414.29 | 1380.96 | 4 | 33.4373
120051 | Vernon Dr | At East Pender St, at North junction, West side of street | 44.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 414.29 | 414.29 | 1 | 9.3519
130001 | Carrall St | Between Expo Boulevard and Keefer St - West (4 Planter Boxes) - Close to Keefer St. | 44.7 | 1 | 276.19 | 1 | 276.19 | 1 | 414.29 | 1 | 276.19 | 1 | 414.29 | 1657.15 | 5 | 37.0727
130003 | Carrall St | Between Expo Boulevard and Pacific Boulevard, East Side | 50.8 | 1 | 514.51 | 1 | 514.51 | 1 | 771.77 | 1 | 514.51 | 1 | 771.77 | 3087.07 | 5 | 60.7691
130002 | Carrall St | Between Expo Boulevard and Keefer St - East (3 Planter Boxes) - Close to Expo Boulevard | 51.2 | 1 | 514.51 | 1 | 514.51 | 1 | 771.77 | 1 | 514.51 | 1 | 771.77 | 3087.07 | 5 | 60.2943
130004 | Carrall St | Between Expo Boulevard and Pacific Boulevard, West Side | 51.5 | 1 | 514.51 | 1 | 514.51 | 1 | 771.77 | 1 | 514.51 | 1 | 771.77 | 3087.07 | 5 | 59.9431
110115 | Brigadoon Ave | Near Duff Street | 51.9 | 1 | 514.51 | 1 | 514.51 | 1 | 771.77 | 1 | 514.51 | 1 | 771.77 | 3087.07 | 5 | 59.4811
130103 | Richards St | Between Pacific St. and Drake St. - Block H Bioswale | 53.5 | 1 | 514.51 | 1 | 514.51 | 1 | 771.77 | 1 | 514.51 | 1 | 771.77 | 3087.07 | 5 | 57.7022
110103 | Quebec St | At Central St, Southeast Corner | 54.7 | 1 | 514.51 | 1 | 514.51 | 1 | 771.77 | 1 | 514.51 | 1 | 771.77 | 3087.07 | 5 | 56.4364
110104 | Quebec St | At Switchmen Street, Southwest Corner | 58.1 | 1 | 514.51 | 1 | 514.51 | 1 | 771.77 | 1 | 514.51 | 1 | 771.77 | 3087.07 | 5 | 53.1337
110101 | W 64th Ave | At West 63rd Avenue | 117.4 | 1 | 714 | 1 | 714 | 1 | 971 | 1 | 714 | 1 | 971 | 4084 | 5 | 34.7871
110114 | Brigadoon Ave | Near Humm Street | 134.2 | 1 | 714 | 1 | 714 | 1 | 971 | 1 | 714 | 1 | 971 | 4084 | 5 | 30.4322
130018 | E 23rd Ave | Between Prince Edward St and Carolina St (Tupper School, west side) | 143 | 1 | 714 | 1 | 714 | 1 | 971 | 1 | 714 | 1 | 971 | 4084 | 5 | 28.5594
130019 | E 23rd Ave | Between Prince Edward St and Carolina St (Tupper School, east side) | 156.6 | 1 | 914 | 1 | 914 | 1 | 1171 | 1 | 914 | 1 | 1171 | 5084 | 5 | 32.4649
130101 | W 63rd Ave | At Yukon Street | 223.6 | 1 | 914 | 1 | 914 | 1 | 1171 | 1 | 914 | 1 | 1171 | 5084 | 5 | 22.737
59 |  |  | 2051.28 | 42 | 15480.15 | 47 | 16714.66 | 51 | 24632.18 | 47 | 16714.66 | 59 | 27471.9 | 101013.55 | 246 | 55.0628
10140
90873.55
69792.22
0.44735
[7 empty] | 56826.99 |  |  | 26110.52
[7 empty] | 6280 |  |  | 82937.51 | 0.18835
[7 empty] | 230.99 | 276.19 | 514.51 | 714 | 914
[7 empty] | 346.49 | 414.29 | 771.77 | 971 | 1171
[7 empty] | 26.8593 | 11.0476 | 10.2902 | 7.14 | 6.0933
[7 empty] | 9.2767 | 5.5349 | 5.1503 | 4.7632 | 4.0877
[7 empty] | 40.2895 | 16.5716 | 15.4354 | 9.71 | 7.8067
[7 empty] | 13.9153 | 8.3024 | 7.7254 | 6.4777 | 5.237

## Inlet Maintenance
GRI ID | Pre-treatment Type | Street Name | Address Description | Oct-24 | Nov-24 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Totals
120002 | River rock | Arbutus St | At W 8th, NE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120003 | River rock | Balsam St | At E Broadway, NW Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120004 | River rock | Balsam St | At W 6th Ave | 35 | 35 | 35 | 35 | 35 | 35 | 210
120216 | sediment pad | Blenheim St | At Quesnel Drive, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120005 | River rock | Blenheim St | At West 20th Ave, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120006 | River rock | Blenheim St | At West 22nd Ave, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120007 | River rock | Blenheim St | At West 23rd Ave, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120008 | River rock | Blenheim St | At West 24th Ave, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120009 | River rock | Blenheim St | At West 26th Ave, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120010 | River rock | Blenheim St | At West 27th Ave, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
110114 | River rock | Brigadoon Ave | Near Humm Street | 35 | 35 | 35 | 35 | 35 | 35 | 210
110115 | River rock | Brigadoon Ave | Near Duff Street | 35 | 35 | 35 | 35 | 35 | 35 | 210
120201 | sediment pad | Campbell Ave | At Union St, Northwest Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
130001 | sediment pad | Carrall St | Between Expo Boulevard and Keefer St - West (4 Planter Boxes) - Close to Keefer St. | 35 | 35 | 35 | 35 | 35 | 35 | 210
130002 | sediment pad | Carrall St | Between Expo Boulevard and Keefer St - East (3 Planter Boxes) - Close to Expo Boulevard | 35 | 35 | 35 | 35 | 35 | 35 | 210
130003 | sediment pad | Carrall St | Between Expo Boulevard and Pacific Boulevard, East Side | 35 | 35 | 35 | 35 | 35 | 35 | 210
130004 | sediment pad | Carrall St | Between Expo Boulevard and Pacific Boulevard, West Side | 35 | 35 | 35 | 35 | 35 | 35 | 210
120018 | River rock | Charles St | At Penticton St, NE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120019 | sediment pad | Comox St | At Bidwell St, NE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120020 | sediment pad | Comox St | At Bute St, NW Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120021 | sediment pad | Comox St | At Gilford St, SW Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120022 | sediment pad | Comox St | At Nicola St, NE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120213 | sediment pad | Cook St. | 1715 Cook St. | 35 | 35 | 35 | 35 | 35 | 35 | 210
120090 | sediment pad | E 14th Ave | At Woodland Dr, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120089 | sediment pad | E 14th Ave | At Woodland Dr, NE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
110102 | sediment pad | E 1st Ave | At Quebec Street, Northwest Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
130018 | sediment pad | E 23rd Ave | Between Prince Edward St and Carolina St (Tupper School) | 35 | 35 | 35 | 35 | 35 | 35 | 210
130019 | sediment pad | E 23rd Ave | Between Prince Edward St and Carolina St (Tupper School) | 35 | 35 | 35 | 35 | 35 | 35 | 210
120203 | sediment pad | E 45th Ave | At Inverness St, NE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120204 | sediment pad | E 45th Ave | At Inverness St, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120034 | River rock | E 50th Ave | At Ontario St, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120088 | sediment pad | E 57th Ave | At Ross St, Southwest Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
130104 | sediment pad | Gilford Street | Gilford Street between Haro Street and Rosemary Brown Lane | 35 | 35 | 35 | 35 | 35 | 35 | 210
110117 | sediment pad | Haro Street | Haro Street at Bute Street | 35 | 35 | 35 | 35 | 35 | 35 | 210
120209 | sediment pad | Haro Street | Haro Street at Broughton Street | 35 | 35 | 35 | 35 | 35 | 35 | 210
120210 | sediment pad | Haro Street | Haro Street at Jervis Street | 35 | 35 | 35 | 35 | 35 | 35 | 210
120205 | sediment pad | Inverness | At E 45th Ave, Southwest Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120037 | sediment pad | Kerr St | Between East Kent Ave South and Riverwalk Ave | 35 | 35 | 35 | 35 | 35 | 35 | 210
120038 | sediment pad | Kinross St | At North Arm Ave, NE Corner (on Kinross) | 35 | 35 | 35 | 35 | 35 | 35 | 210
120040 | River rock | Larch St | At Broadway | 35 | 35 | 35 | 35 | 35 | 35 | 210
120054 | sediment pad | Nicola St | At Comox St, SW Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120046 | sediment pad | North Arm Ave | At Kinross St, NE Corner (on N Arm Ave) | 35 | 35 | 35 | 35 | 35 | 35 | 210
120048 | sediment pad | North Arm Ave | Between Kinross and Jack Uppal, south side mid-block | 35 | 35 | 35 | 35 | 35 | 35 | 210
120049 | sediment pad | North Arm Ave | Between Kinross and Jack Uppal, north side mid-block | 35 | 35 | 35 | 35 | 35 | 35 | 210
120091 | sediment pad | Ontario St | At E 42nd Ave, NE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120092 | sediment pad | Ontario St | At E 42nd Ave, NW Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120093 | sediment pad | Ontario St | At E 42nd Ave, SW Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120094 | sediment pad | Ontario St | At E 43rd Ave, NE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
110121 | sediment pad | Ontario St | at 16th Ave | 35 | 35 | 35 | 35 | 35 | 35 | 210
110006 | sediment pad | Pierview Crescent | At East Kent Ave North, NW Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
110007 | sediment pad | Pierview Crescent | At East Kent Ave North, Northerly Bioswale closer to turning circle | 35 | 35 | 35 | 35 | 35 | 35 | 210
120207 | sediment pad | Pine St | At W 7th Ave, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
110108 | sediment pad | Prince Edward St | Between E 51st Ave and E 53rd Ave @ Sunset Park | 35 | 35 | 35 | 35 | 35 | 35 | 210
110103 | sediment pad | Quebec St | At Central St, Southeast Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
110104 | sediment pad | Quebec St | At Switchmen Street, Southwest Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
110105 | sediment pad | Quebec St | At E 1st Avenue, Northeast Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
110106 | sediment pad | Quebec St | At E 1st Avenue, Southeast Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
110107 | sediment pad | Quebec St | At Switchmen Street, Northeast Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120056 | sediment pad | Rhodes St | At E 41st Ave, SW corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120058 | sediment pad | Rhodes St | At E 41st Ave, SE corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120080 | sediment pad | Riverwalk Ave | Between Kinross St and Kerr St, North side at Kerr St | 35 | 35 | 35 | 35 | 35 | 35 | 210
120081 | sediment pad | Riverwalk Ave | Between Kinross St and Kerr St, South side at Kerr St | 35 | 35 | 35 | 35 | 35 | 35 | 210
120082 | sediment pad | Riverwalk Ave | Between Kinross St and Kerr St, North side, 2nd BB from Kerr St | 35 | 35 | 35 | 35 | 35 | 35 | 210
120083 | sediment pad | Riverwalk Ave | Between Kinross St and Kerr St, South side, 2nd BB from Kerr St | 35 | 35 | 35 | 35 | 35 | 35 | 210
120084 | sediment pad | Riverwalk Ave | Between Kinross St and Kerr St, South side, 3rd BB from Kerr St | 35 | 35 | 35 | 35 | 35 | 35 | 210
120085 | sediment pad | Riverwalk Ave | Between Kinross St and Kerr St, North side, 3rd BB from Kerr St | 35 | 35 | 35 | 35 | 35 | 35 | 210
120086 | sediment pad | Riverwalk Ave | Between Kinross St and Kerr St, South side, 4th BB from Kerr St | 35 | 35 | 35 | 35 | 35 | 35 | 210
120087 | sediment pad | Riverwalk Ave | Between Kinross St and Kerr St, North side, 4th BB from Kerr St | 35 | 35 | 35 | 35 | 35 | 35 | 210
120072 | sediment pad | Sawmill Crescent E | Between River District Crossing and Marine Way | 35 | 35 | 35 | 35 | 35 | 35 | 210
120073 | sediment pad | Sawmill Crescent E | Between River District Crossing and Marine Way | 35 | 35 | 35 | 35 | 35 | 35 | 210
120074 | sediment pad | Sawmill Crescent E | Between River District Crossing and Marine Way | 35 | 35 | 35 | 35 | 35 | 35 | 210
120075 | sediment pad | Sawmill Crescent E | Between River District Crossing and Marine Way | 35 | 35 | 35 | 35 | 35 | 35 | 210
120076 | sediment pad | Sawmill Crescent E | Between River District Crossing and Marine Way | 35 | 35 | 35 | 35 | 35 | 35 | 210
120077 | sediment pad | Sawmill Crescent E | Between River District Crossing and Marine Way | 35 | 35 | 35 | 35 | 35 | 35 | 210
120097 | sediment pad | Tisdall St | At W 48 Ave, Northeast Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120098 | sediment pad | Tisdall St | At W 48 Ave, Northwest Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120057 | River rock | Trafalgar St | At Broadway, SW Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120059 | River rock | Trafalgar St | At Broadway, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120062 | River rock | W 12th Ave | At Trafalgar St, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120063 | River rock | W 16th Ave | At Willow St (NE corner) | 35 | 35 | 35 | 35 | 35 | 35 | 210
120108 | sediment pad | W 16th Ave | At Manitoba St (NE Corner) | 35 | 35 | 35 | 35 | 35 | 35 | 210
120041 | River rock | W 19th Ave | At Laurel St, NW Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120042 | River rock | W 19th Ave | At Laurel St, SW Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120060 | sediment pad | W 42nd Ave | At Ontario St, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120099 | sediment pad | W 59th Ave | At Ross St | 35 | 35 | 35 | 35 | 35 | 35 | 210
130101 | sediment pad | W 63rd Ave | At Yukon Street | 35 | 35 | 35 | 35 | 35 | 35 | 210
110101 | sediment pad | W 64th Ave | At West 63rd Avenue | 35 | 35 | 35 | 35 | 35 | 35 | 210
120208 | sediment pad | W 7th Ave | At Pine St, NE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120206 | sediment pad | W 8th Ave | At Pine St, NE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120064 | River rock | Willow St | At W 16th Ave, NW corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120102 | sediment pad | Windsor St | Between E 24th and E 23rd Ave | 35 | 35 | 35 | 35 | 35 | 35 | 210
120103 | sediment pad | Windsor St | At E 22nd Ave, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
110122 | sediment pad | Woodland | 2nd Ave | 35 | 35 | 35 | 35 | 35 | 35 | 210
120104 | sediment pad | Woodland Dr | At E 14th Ave, NW Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120105 | sediment pad | Woodland Dr | At E 14th Ave, NE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120106 | sediment pad | Woodland Dr | At E 14th Ave, SW Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
120107 | sediment pad | Woodland Dr | At E 14th Ave, SE Corner | 35 | 35 | 35 | 35 | 35 | 35 | 210
Totals |  |  |  | 3395 | 3395 | 3395 | 3395 | 3395 | 3395 | 20370
|  |  |  | 10185 | [5 empty] | 39238